## Slide 1: WebIQ Project
Current status and next steps

## Slide 2: Migration Tools
Delphi Parser
  Custom script VCL_To_UniGUI.txt (85% - initial goal – ongoing after that)
  Additional script rule for migrating TwwDBGrid & IQSearch to IQUniGridControl (100%)
  Changes to take into account class inheritance while applying the rules (SCA.DB used for querying class inheritance)
    100% - initial goal
    Require more changes to SCA, SCA.DB, and DP (0% - 24 hrs)
  Several improvements to enhance performance (1.7 minutes / file) (100%)
RemoveUsesScan (100%, needs testing)
  Fixed and improved the original source code to correctly remove all unused units
  Added the functionality of renaming units and explicit unit references.
  Improved performance (initial scanning takes up to 3 minutes + 1 min / PAS file)

## Slide 3: Behind the scenes
IQWebVCL package
  Every component in IQVCL was replicated to IQWebVCL with a different name but similar public and published properties. (100%)
  Most of the components are just empty stubs, waiting to be implemented using UniGUI components. (still need to be converted, i.e. filled in with code)
  Security System, DB Changes and UI element mappings
  Share Folder (113 forms + 148 units – 0%)
  In the process, several units were renamed using namespaces. (100%)
  Both IQVCL and IQWebVCL can be installed in the IDE, giving the option of loading the original and migrated forms while finishing with the manual migration process. (100%)
Many units trigger visual actions which also need to be migrated to UniGUI – 0%

## Slide 4: Recommended steps
Create a Knowledge Base (Wiki) for the migration process
  Document the tools
  Publish an Excel spreadsheet to register the progress (and use it for improving the time estimates both for non-migrated units / forms and the whole project)
  Create and start documenting typical migration issues with their solution
  Document the migration process
Finish testing and tuning the tools by migrating a sample of units and forms
  Add rules for removing properties according to messages from Delphi (when loading migrated forms)
Create a snapshot of IQWin32 to WebIQ\ModulesWin
  If possible, start by running RemoveUsesScan for IQWin32 and confirm that everything compiles.
  Task a developer with periodical (daily / weekly) comparisons between IQWin32 and the snapshot
    If something changed but the changed files were not migrated, just update ModulesWin
    Otherwise, try to merge the changes to the migrated code or create an issue for delegating that job
Migrate the code by pieces (forms / units or modules) by using Delphi Parser and manual changes (interacting with the Knowledge Base)
As a parallel task, finish implementing IQWebVCL, implement the new IQShare, and add global features to the supporting framework like Security, UI persistence, exception handling, etc.

## Slide 5: Estimates
Source Code Analyzer
  Using Castalia Parser we populate SCA.DB with class inheritance and unit statistics.
  Key statistics like the amount and type of members / fields in a class are not collected.
  We can also collect calls to ShowModal.
Estimating Points
  One or more experts can assign points as a measure of complexity to a sample of forms / units, but having almost 4,400 of them we will need to estimate how many points to assign to whatever is left.
  The statistics collected with SCA should provide enough information to model the complexity based on them as independent variables.
  Once we build the model, we will use it to have “points” assigned for all forms / units.
Velocity
  Based on developer’s progress report we will establish velocity and provide updated estimates of project completion, which will get better over time.